## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US-00 | User Registration and Login | As any user (TA applicant, module organiser, or admin), I want to register an account and log in to the system so that I can access role-specific features and maintain my personal data securely. | High | 1 | 1.User can register with student/staff ID, password, and select role; 2.Required fields (ID, password, role) are validated; ID format is checked; 3.User can log in with registered ID and password. 4.System identifies user role after login and redirects to role-specific dashboard. 5.User can log out and session is terminated.Meanwhile, all modified content will be stored. | 5 | Foundational feature | 2026-03-23 | 2026-03-25
US-01 | Create Applicant Profile | As a TA applicant, I want to create my personal profile so that I can show my personal information when applying for suitable jobs. | High | 1 | 1.User can enter name, age, gender, education, expected salary, and desired positions; 2.Required fields are validated; 3.Profile is saved successfully. | 3 | Core feature | 2026-03-25 | 2026-03-26
US-02 | Upload CV | As a TA applicant, I want to upload my CV so that module organisers can review my qualifications and match me with suitable positions. | High | 1 | 1.User can choose and upload a CV; 2.System only accepts allowed file types and sizes; 3.Uploaded CV is linked to the profile. | 3 | Core feature | 2026-03-25 | 2026-03-26
US-03 | Browse Available Jobs | As a TA applicant, I want to browse available jobs so that I can find positions that match my skills, schedule and working expectations. | High | 1 | 1.User can view the list of available jobs; 2.Only open jobs are displayed; 3.Key job information is shown. | 2 | Core feature | 2026-03-29 | 2026-03-30
US-04 | Apply for a Job | As a TA applicant, I want to send my application together with my CV to the employer so that I can be considered for the role. | High | 1 | 1.User can submit an application from a job page; 2.System links the application to the applicant and the job; 3.Confirmation is displayed; 4. Prevent duplicate applications to the same job (handled by system validation) | 3 | Core feature | 2026-04-01 | 2026-04-02
US-05 | Edit Applicant Profile | As a TA applicant, I want to edit my profile so that my information stays accurate. | Medium | 2 | 1.User can edit key personal information; 2.Required fields are validated; 3.Updated profile is saved successfully. | 2 | Depends on US-01 | 2026-04-06 | 2026-04-07
US-06 | View Application Status | As a TA applicant, I want to view my application status so that I know whether I am shortlisted, accepted, or rejected. | High | 2 | 1.User can view all submitted applications; 2.Each application shows current status; 3.Status updates are displayed correctly. | 2 | Core feature | 2026-04-11 | 2026-04-12
US-07 | Search and Filter Jobs | As a TA applicant, I want to search or filter jobs so that I can quickly find relevant opportunities I'm interested in. | Medium | 3 | 1.User can filter jobs by module or activity type and search by keyword; 2.Results are updated correctly. | 3 | Usability improvement | 2026-04-20 | 2026-04-22
US-08 | Contact Module Organiser | As a TA applicant, I want to contact the module organiser regarding a position so that I can clarify specific recruitment details based on my personal situation. | Medium | 3 | 1.Applicants can send a message or inquiry to the module organiser via the system; 2.System records the inquiry and allows module organiser to reply; 3.Applicants receive notification of replies; | 3 | Usability improvement | 2026-04-23 | 2026-04-25
US-09 | Skill Matching Recommendation | As a TA applicant, I want the system to recommend suitable jobs based on my skills so that I can apply more efficiently. | Low | 4 | 1.System recommends suitable jobs based on applicant skills; 2.Recommended jobs and reason for recommendation are displayed. | 8 | AI-assisted feature; implementation difficulty high | 2026-05-04 | 2026-05-09
US-10 | Missing Skills Feedback | As a TA applicant, I want to know which required skills I am missing so that I can improve before applying. | Low | 4 | 1.System identifies missing skills for a selected job; 2.Feedback is displayed clearly; 3.Result is explainable. | 5 | AI-assisted feature; implementation difficulty high | 2026-05-10 | 2026-05-13
US-11 | Post a Job | As a module organiser, I want to create a job posting so that I can recruit suitable teaching assistants. | High | 1 | 1.Module organiser can create a job posting with title, description, required skills, and workload; 2.Required fields are validated; 3.Job is saved and visible to applicants. | 5 | Core feature | 2026-03-25 | 2026-03-28
US-12 | Edit or Close a Job | As a module organiser, I want to edit or close a job posting so that my updated requirements are visible to applicants, and outdated vacancies are no longer displayed. | Medium | 2 | 1.Module organiser can update job details; 2.Can mark a job as closed; 3.Closed jobs are no longer open for application. | 2 | Admin control | 2026-04-08 | 2026-04-09
US-13 | Review Applications | As a module organiser, I want to see all applicants for a job so that I can compare candidates and make decisions. | High | 2 | 1.Module organiser can view the list of applicants and their CVs for a job; 2.Applications are correctly linked to the job. | 3 | Core feature | 2026-04-08 | 2026-04-10
US-14 | Shortlist or Select Applicant | As a module organiser, I want to shortlist or select an applicant so that I can fill the job efficiently and show my selective outcomes. | High | 2 | 1.Module organiser can change application status to shortlisted/accepted/rejected; 2.Applicant can see updated status. | 1 | Core feature | 2026-04-10 | 2026-04-11
US-15 | Check TA Workload | As an admin, I want to check a TA’s overall workload so that I can avoid allocating too many hours and workloads to just one TA. | High | 2 | 1. Admin can view overall workload for each TA 2. Display: assigned jobs, total hours, schedules 3. Highlight overloaded TAs (>20 hours/week) 4. Show schedule conflicts | 5 | Mandatory suggested function | 2026-04-13 | 2026-04-15
US-16 | Prevent Schedule Conflict | As an admin, I want to prevent an applicant from applying to positions with overlapping schedules so that TAs can fulfill all their commitments | High | 3 | 1. System retrieves applicant's current workload from US-15 2. System checks if new application's schedule conflicts with existing accepted jobs 3. If conflict exists, application is blocked with clear error message 4. Applicant can see which job conflicts and the overlapping time slots 5. System also checks if total hours exceed maximum limit (e.g., 20 hours/week) | 8 | Mandatory function | 2026-04-19 | 2026-04-25