## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US-00 | User Registration and Login | As any user (TA applicant, module organiser, or admin), I want to register an account and log in to the system so that I can access role-specific features and maintain my personal data securely. | High | 1 | 1.User can register with student/staff ID, password, and select role; 2.Required fields (ID, password, role) are validated; ID format is checked; 3.User can log in with registered ID and password; 4.System identifies user role after login and redirects to role-specific dashboard; 5.User can log out and session is terminated; all modified content is stored. | 5 | Foundational feature | 2026-03-23 | 2026-03-25
US-01 | Create Applicant Profile | As a TA applicant, I want to create my personal profile so that I can show my personal information when applying for suitable jobs. | High | 1 | 1.User can enter name, age, gender, education, expected salary, and desired positions; 2.Required fields are validated; 3.Profile is saved successfully. | 3 | Core feature | 2026-03-25 | 2026-03-27
US-02 | Submit CV | As a TA applicant, I want to provide my CV so that module organisers can review my qualifications. | High | 1 | 1.Applicant can paste CV content or upload a .txt CV file; 2.System validates required content and file format constraints; 3.CV is stored and linked to the applicant profile. | 3 | Core feature | 2026-03-25 | 2026-03-27
US-03 | Browse Open Jobs | As a TA applicant, I want to browse available jobs so that I can find suitable opportunities. | High | 1 | 1.Applicant can view a list of open jobs only; 2.Each job shows title, module/activity, required skills, workload, and schedule; 3.Closed jobs are not shown in the open jobs list. | 2 | Core feature | 2026-03-28 | 2026-03-30
US-04 | Apply for a Job | As a TA applicant, I want to apply for an open job with my profile and CV so that I can be considered for the role. | High | 1 | 1.Applicant can submit an application from a job page; 2.System links the application to the applicant and the selected job; 3.Only open jobs can be applied for; 4.Duplicate applications to the same job are blocked; 5.Confirmation is displayed after successful submission. | 3 | Core feature | 2026-03-31 | 2026-04-02
US-05 | Edit Applicant Profile | As a TA applicant, I want to edit my profile so that my information remains accurate. | Medium | 2 | 1.Applicant can update key personal information, skills, availability, and desired positions; 2.Required fields are validated; 3.Updated profile is saved successfully. | 2 | Depends on US-01 | 2026-04-06 | 2026-04-07
US-06 | View Application Status | As a TA applicant, I want to view my application status so that I know the progress of my applications. | High | 2 | 1.Applicant can view all submitted applications; 2.Each application shows job title, submission date, and current status; 3.Status updates are displayed correctly based on the latest saved data. | 2 | Core feature | 2026-04-06 | 2026-04-08
US-07 | Search and Filter Jobs | As a TA applicant, I want to search and filter jobs so that I can quickly find relevant opportunities. | Medium | 3 | 1.Applicant can search by keyword and filter by module, activity type, required skill, or time slot; 2.Results update correctly and only include currently open jobs. | 3 | Usability improvement | 2026-04-20 | 2026-04-22
US-08 | Contact Module Organiser | As a TA applicant, I want to send an inquiry about a job so that I can clarify details before applying. | Medium | 3 | 1.Applicant can send a message linked to a specific job; 2.Module organiser can view and reply within the system; 3.Applicant can view the organiser's reply in the system. | 5 | Useful but non-core; scope should stay simple | 2026-04-20 | 2026-04-25
US-09 | Job Recommendation Based on Skills | As a TA applicant, I want the system to recommend suitable jobs based on my profile and skills so that I can apply more efficiently. | Low | 4 | 1.System compares applicant skills and profile data with open job requirements; 2.Recommended jobs are displayed with brief reasons such as matched skills or suitable availability; 3.Results are explainable. | 8 | AI-assisted or rule-based plus AI explanation | 2026-05-04 | 2026-05-10
US-10 | Missing Skills Feedback | As a TA applicant, I want to know which skills I am missing for a selected job so that I can improve before applying. | Low | 4 | 1.System compares the applicant profile with the selected job requirements; 2.Missing or weakly matched skills are displayed clearly; 3.Feedback includes an understandable explanation. | 5 | AI-assisted or rule-based plus AI explanation | 2026-05-11 | 2026-05-15
US-11 | Post a Job | As a module organiser, I want to create a job posting so that I can recruit suitable teaching assistants. | High | 1 | 1.Module organiser can create a job with title, module/activity, description, required skills, workload, and schedule; 2.Required fields are validated; 3.Job is saved successfully and becomes visible to applicants as an open job. | 5 | Core feature | 2026-03-25 | 2026-03-29
US-12 | Edit or Close a Job | As a module organiser, I want to update or close a job posting so that applicants can see current requirements only. | Medium | 2 | 1.Module organiser can edit job details; 2.Module organiser can mark a job as closed; 3.Closed jobs are no longer available for new applications but existing applications remain visible for review. | 2 | Job management by MO | 2026-04-08 | 2026-04-09
US-13 | Review and Process Applications | As a module organiser, I want to review applicants and update their status so that I can make hiring decisions efficiently. | High | 2 | 1.Module organiser can view all applications for a job together with applicant profiles and CVs; 2.Applications are correctly linked to the job; 3.Organiser can change status to Shortlisted, Accepted, or Rejected; 4.Applicants can see updated status after the change is saved. | 5 | Core feature; merged from Review Applications and Shortlist/Select stories | 2026-04-08 | 2026-04-13
US-14 | Check TA Workload | As an admin, I want to check each TA's overall workload so that I can avoid over-allocation. | High | 2 | 1.Admin can view each accepted TA's assigned jobs, total weekly hours, and schedules; 2.The system highlights overloaded TAs whose workload exceeds the weekly limit; 3.Schedule conflicts are shown clearly. | 8 | Mandatory suggested function | 2026-04-11 | 2026-04-17
US-15 | Prevent Schedule Conflict | As a TA applicant, I want the system to prevent me from applying for jobs that conflict with my accepted schedule so that I do not take impossible commitments. | High | 3 | 1.Before saving a new application, the system checks the applicant's accepted jobs and total weekly hours; 2.If schedule overlap exists, the application is blocked with a clear message; 3.The conflicting job and overlapping time slot are shown; 4.If the workload limit is exceeded, the application is also blocked with an explanation. | 8 | Mandatory function; depends on US-11 (schedule data) and US-14 (workload data) | 2026-04-24 | 2026-05-02