## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US-01 | Create Applicant Profile | As a TA applicant, I want to create my personal profile so that I can show my personal information when applying for suitable jobs. | High | 1 | 1.User can enter name, age, gender, education, expected salary, and desired positions; 2.Required fields are validated; 3.Profile is saved successfully. | 3 | Core feature
US-02 | Edit Applicant Profile | As a TA applicant, I want to edit my profile so that my information stays accurate. | Medium | 2 | 1.User can edit key personal information; 2.Required fields are validated; 3.Updated profile is saved successfully. | 2 | Depends on US-01
US-03 | Upload CV | As a TA applicant, I want to upload my CV so that module organisers can review my qualifications and match me with suitable positions. | High | 1 | 1.User can choose and upload a CV; 2.System only accepts allowed file types and sizes; 3.Uploaded CV is linked to the profile. | 3 | Core feature
US-04 | Browse Available Jobs | As a TA applicant, I want to browse available jobs so that I can find positions that match my skills, schedule and working expectations. | High | 1 | 1.User can view the list of available jobs; 2.Only open jobs are displayed; 3.Key job information is shown. | 3 | Core feature
US-05 | Search and Filter Jobs | As a TA applicant, I want to search or filter jobs so that I can quickly find relevant opportunities I'm interested in. | Medium | 3 | 1.User can filter jobs by module or activity type and search by keyword; 2.Results are updated correctly. | 3 | Usability improvement
US-06 | Apply for a Job | As a TA applicant, I want to send my application together with my CV to the employer so that I can be considered for the role. | High | 1 | 1.User can submit an application from a job page; 2.System links the application to the applicant and the job; 3.Confirmation is displayed; 4.Cannot apply to more than two positions simultaneously. | 5 | Core feature
US-07 | View Application Status | As a TA applicant, I want to view my application status so that I know whether I am shortlisted, accepted, or rejected. | High | 2 | 1.User can view all submitted applications; 2.Each application shows current status; 3.Status updates are displayed correctly. | 3 | Core feature
US-08 | Skill Matching Recommendation | As a TA applicant, I want the system to recommend suitable jobs based on my skills so that I can apply more efficiently. | Low | 4 | 1.System recommends suitable jobs based on applicant skills; 2.Recommended jobs and reason for recommendation are displayed. | 8 | AI-assisted feature; implementation difficulty high
US-09 | Missing Skills Feedback | As a TA applicant, I want to know which required skills I am missing so that I can improve before applying. | Low | 4 | 1.System identifies missing skills for a selected job; 2.Feedback is displayed clearly; 3.Result is explainable. | 5 | AI-assisted feature; implementation difficulty high
US-10 | Contact Module Organiser | As a TA applicant, I want to contact the module organiser regarding a position so that I can clarify specific recruitment details based on my personal situation. | Medium | 2 | 1.Applicants can send a message or inquiry to the module organiser via the system; 2.System records the inquiry and allows module organiser to reply; 3.Applicants receive notification of replies; | 3 | Usability improvement
US-11 | Post a Job | As a module organiser, I want to create a job posting so that I can recruit suitable teaching assistants. | High | 1 | 1.Module organiser can create a job posting with title, description, required skills, and workload; 2.Required fields are validated; 3.Job is saved and visible to applicants. | 5 | Core feature
US-12 | Edit or Close a Job | As a module organiser, I want to edit or close a job so that some changes on my requirements can be seen, and some outdated vacancies cannot be seen. | Medium | 3 | 1.Module organiser can update job details; 2.Can mark a job as closed; 3.Closed jobs are no longer open for application. | 3 | Admin control
US-13 | Review Applications | As a module organiser, I want to see all applicants for a job so that I can compare candidates and make decisions. | High | 2 | 1.Module organiser can view the list of applicants and their CVs for a job; 2.Applications are correctly linked to the job. | 5 | Core feature
US-14 | Shortlist or Select Applicant | As a module organiser, I want to shortlist or select an applicant so that I can fill the job efficiently and show my selective outcomes. | High | 2 | 1.Module organiser can change application status to shortlisted/accepted/rejected; 2.Applicant can see updated status. | 5 | Core feature
US-15 | Check TA Workload | As an admin, I want to check a TA’s overall workload so that I can avoid allocating too many hours and workloads to just one TA. | High | 2 | 1.Admin can view overall workload for each TA; 2.Assigned jobs or hours are displayed; 3.Overloaded TAs can be identified. | 5 | Mandatory suggested function
US-16 | Prevent Duplicate Applications | As an admin, I want to prevent duplicate applications to the same job so that application records remain accurate. | Medium | 2 | 1.The same applicant cannot apply to the same job twice; 2.Warning is shown; 3.Original application remains unchanged. | 2 | Validation rule
US-17 | Prevent Multiple Applications | As an admin, I want to prevent an applicant from applying to multiple positions simultaneously so that no single TA is overloaded and more applicants have the opportunity to get a job. | High | 2 | 1.The system does not allow an applicant to apply to more than two positions at the same time; 2.A warning is displayed if an applicant tries; 3.Original application remains unchanged. | 5 | Mandatory function